## Slide 1: Software Engineering Process
“spiral” by Till Krech is licensed under CC BY-NC-ND 2.0 / Cropped from original
Notes: “spiral” by Till Krech is licensed under CC BY-NC-ND 2.0 / Cropped from original
https://flic.kr/p/7u4Xr2

## Slide 2: Engineering software is a Big Job
Many requirements to gather
Many aspects to design
Many features to construct
Many tests to write and run
And much more!
“University Bridge under construction, 1932” by Seattle Municipal Archives is licensed under CC BY 2.0 / Cropped from original
Notes: “University Bridge under construction, 1932” by Seattle Municipal Archives is licensed under CC BY 2.0 / Cropped from original
https://flic.kr/p/7jKWYt

## Slide 3: Practical Issue
What order should tasks be done in?
That is, what process to use?

## Slide 4: The Classic Way: Waterfall
AKA Sequential Process Model
Requirements
Design
Implementation
Verification
Maintenance
“Waterfall Model” by Paul Smith / Paulsmith99 at en.wikipedia is licensed under CC BY 3.0
⚠️
But often a bad way
Notes: “Waterfall Model” by Paul Smith / Paulsmith99 at en.wikipedia is licensed under CC BY 3.0
http://en.wikipedia.org/wiki/File:Waterfall_model_%281%29.svg

## Slide 5: What could go wrong?
Requirements
Design
Implementation
Verification
6 months
6 months
6 months
6 months
Release!

## Slide 6: What could go wrong?
Requirements
Design
Implementation
Verification
6 months
6 months
6 months
6 months
Release!
I don’t like it…
Customer
Problem!

## Slide 7: Why Waterfall Fails
False assumption: Specifications are …
  predictable – can be correctly defined at the start
  stable – have low change rates
Actual stats:
  25% of requirements changed 😱
  35% to 50% changed in large projects 😱 😱

## Slide 8: Solution: Empirical Process Model
Feedback
Adaptation
em·pir·i·cal
/imˈpirək(ə)l/
adjective
based on, concerned with, or verifiable by observation or experience rather than theory or pure logic.
Source: https://languages.oup.com/google-dictionary-en/

## Slide 9: Iterative & Incremental Development Process
Planning
Requirements
Analysis &
Design
Implementation
Deployment
Testing
Evaluation
Initial
Planning

## Slide 10: Iterative & Incremental Development Process
Planning
Requirements
Analysis &
Design
Implementation
Deployment
Testing
Evaluation
Initial
Planning
repeated cycles

## Slide 11: Iterative & Incremental Development Process
Planning
Requirements
Analysis &
Design
Implementation
Deployment
Testing
Evaluation
Initial
Planning
build up small portions at a time

## Slide 12: Iterative & Incremental Development Process
Planning
Requirements
Analysis &
Design
Implementation
Deployment
Testing
Evaluation
Initial
Planning
Where are
feedback
&
adaptation?

## Slide 13: Iterative & Incremental Development Process
Planning
Requirements
Analysis &
Design
Implementation
Deployment
Testing
Evaluation
Initial
Planning
Feedback
Adaptation

## Slide 14: Iterative & Incremental Development: Key Benefits
Visible early progress
  No “analysis paralysis”
Fail fast
  Catch changing requirements quickly
Course correct quickly
  Reduce wasted effort
Iterative process improvement

## Slide 15: Iteration Length?
Short is good
2 to 6 weeks
1 is too short for good feedback
Too long undermines benefits
“TIME” by becosky... is licensed under CC BY-SA 2.0 / Cropped from original
Notes: “TIME” by becosky... is licensed under CC BY-SA 2.0 / Cropped from original
https://flic.kr/p/632Ye5

## Slide 16: Our Project Iterations?
Planning
Requirements
Analysis &
Design
Implementation
Deployment
Testing
Evaluation
Initial
Planning
M0
M1

## Slide 17: Summary
Software Engineering Process
Waterfall Process Model
Empirical Process Model
Iterative & Incremental Development
“spiral” by Till Krech is licensed under CC BY-NC-ND 2.0 / Cropped, darkened from original

## Slide 18: Appendix: Extras

## Slide 19
Choose USs for Iteration
Divide Chosen USs into Tasks
Assign Tasks to Workers
Get to Work!
Developer
Customer
Create USs
Requirements
Estimate USs
USs + Estimates
Prioritize USs
USs + Estimates + Priorities

## Slide 20: Estimation is Hard
http://xkcd.com/1658/

## Slide 21: Principles for Estimation
Principle: Estimates for smaller, more-immediate tasks tend to be more accurate than ones for larger, more-future tasks
Principle: Past performance is the best indicator of future performance
  Approach: Track your outcomes; refine your estimates
Principle: Wisdom of the crowd
  Goal: Predict how events will unfold
    Think event planning
  Problem: Easy to miss something
  Solution: More brains = more opportunities to catch eventualities

## Slide 22: Planning Poker Estimation Using Wisdom of the Crowd
Cards with days of work
For each US:
  Discuss work involved
  Flip cards
  Repeat until consensus
Efficiency in estimating is important
  Don’t expect your estimates to be super accurate

## Slide 23
Here’s a video demonstration of planning poker:
http://youtu.be/0FbnCWWg_NY
Here’s a planning poker web app:
https://planningpokeronline.com/

## Slide 24: Principle: Customer sets priorities
Ensures alignment with customer goals
Helps customer feel in control
  Project isn’t going “off the rails”
Estimates help customer maximize cost-benefit

## Slide 25: Priority Numbering Scheme
Multiples of 10:
  10 - Highest priority
  20
  30
  40
  50
  … - Lowest priority
Non-multiples of 10 may be used if helpful

## Slide 26: So in the end you have…
Collection of user stories
  With estimates
  And customer priorities